Project Planning Phase

Project Planning (Backlog, Sprints & Story Points)

| Date | 18 June 2026 |
| --- | --- |
| Team ID | FSD-ShopEZ-01 |
| Project Name | ShopEZ — Full Stack E-Commerce Platform |

We planned ShopEZ across 4 sprints of 7 days each, moving from core auth and setup in Sprint 1, through products and discovery in Sprint 2, to cart and orders in Sprint 3, and finishing with the seller hub, reviews, and deployment in Sprint 4.

# Product Backlog & Sprint Schedule

| Sprint | Feature Area | Story No. | Task / User Story | Points | Priority | Who |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Project Setup | USN-0 | Express server setup, MongoDB Atlas connection, env config, folder structure | 3 | High | Solo Dev |
| Sprint-1 | Auth | USN-1 | Buyer and Seller registration with role selection | 3 | High | Solo Dev |
| Sprint-1 | Auth | USN-2 | Login with JWT issuance and role-based redirect | 2 | High | Solo Dev |
| Sprint-1 | Auth | USN-3 | Protected routes, authMiddleware, roleMiddleware | 2 | High | Solo Dev |
| Sprint-2 | Products | USN-4 | Seller: add product with Cloudinary image upload | 5 | High | Solo Dev |
| Sprint-2 | Products | USN-5 | Seller: edit and delete own products | 3 | High | Solo Dev |
| Sprint-2 | Products | USN-6 | Buyer: product grid with search, filter by category and price | 4 | High | Solo Dev |
| Sprint-2 | Products | USN-7 | Product detail page with image, info, and reviews section | 3 | High | Solo Dev |
| Sprint-3 | Cart | USN-8 | Redux cart slice — add, update quantity, remove, calculate totals | 4 | High | Solo Dev |
| Sprint-3 | Checkout | USN-9 | Checkout form with shipping address and order summary | 3 | High | Solo Dev |
| Sprint-3 | Orders | USN-10 | Order placement API and confirmation page | 2 | High | Solo Dev |
| Sprint-3 | Orders | USN-11 | Buyer: view order history with status badges | 2 | Medium | Solo Dev |
| Sprint-4 | Seller Hub | USN-12 | Seller: view orders, update order status from dashboard | 3 | High | Solo Dev |
| Sprint-4 | Analytics | USN-13 | Seller analytics — revenue, orders, top products via aggregation | 5 | High | Solo Dev |
| Sprint-4 | Reviews | USN-14 | Buyer: submit star rating and review on product page | 3 | Medium | Solo Dev |
| Sprint-4 | Deploy | USN-15 | Deploy frontend to Vercel, backend to Render, env vars configured | 3 | High | Solo Dev |

# Sprint Tracker & Velocity

| Sprint | Total Points | Duration | Start Date | End Date | Points Done | Actual Release |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 10 | 7 Days | 01 May 2026 | 07 May 2026 | 10 | 07 May 2026 |
| Sprint-2 | 15 | 7 Days | 08 May 2026 | 14 May 2026 | 15 | 14 May 2026 |
| Sprint-3 | 11 | 7 Days | 15 May 2026 | 21 May 2026 | 11 | 21 May 2026 |
| Sprint-4 | 14 | 7 Days | 22 May 2026 | 28 May 2026 | 14 | 28 May 2026 |

Total Story Points: 50  |  Total Duration: 28 Days  |  Average Velocity: 12.5 points per week

The team maintained consistent velocity across all four sprints. No sprint was over-committed and no features were dropped. The solo developer model meant decisions were fast but required discipline to stay on the sprint plan.